## Upgrade Plan
Task | Description | Priority | Solution | Impact
Backup the Project | Create a full backup of the project, including all files and dependencies. | High | Backup project files and dependencies to a secure location. (Azure) | Low - Prevents data loss during upgrade.
Check Dependencies | Identify and list all dependencies in package.json and check their compatibility with Angular 17. | High | Use npm outdated and compatibility documentation to audit dependencies. | Medium - Ensures compatibility and avoids runtime issues.
Check for Deprecated APIs | Angular 17 likely deprecates or removes certain APIs and features present in Angular 14. Identify these changes using the update guide and plan for necessary code modifications. | Medium | Refer to Angular deprecation guides to identify API replacements. | High - Avoids breaking changes and ensures application stability.
Review Browser Support | Ensure targeted browsers are supported by Angular 17. | Medium | Check Angular's browser compatibility documentation. | Low - Validates target environments for application functionality.
Verify Node.js and NPM Versions | Verify Node.js version meets Angular 17 requirements and update if necessary. | High | Ensure Node.js version >= 18 and update NPM to the latest stable version. | High - Essential for running Angular 17.
Upgrade Angular CLI and Core Packages | Run 'ng update @angular/core@17 @angular/cli@17' and resolve conflicts. | High | Run Angular CLI update commands and resolve conflicts as they appear. | High - Ensures project compatibility with Angular 17.
Update TypeScript | Update TypeScript to version 5.x as required by Angular 17. | High | Update TypeScript in package.json or via npm install command. | Medium - Required for Angular 17 features to work.
Upgrade RxJS | Update RxJS to the version required by Angular 17. | High | Angular 17 might require a newer RxJS version. Update RxJS and refactor any affected code, particularly observables and subscriptions. | Medium - RxJS compatibility ensures stable reactive programming.
Update Third-Party Libraries | Check for updates to third-party libraries and ensure compatibility. | High | Review third-party library documentation for compatibility and update accordingly. | High - Prevents runtime or build issues from outdated libraries.
Resolve Breaking Changes | Major version upgrades often introduce breaking changes. We need to refactor code and resolve any conflicts arising from these changes. | High | Refactor code to replace deprecated APIs and test thoroughly. | High - Necessary to prevent runtime and build errors.
Update Unit Tests | Update test configurations and ensure all unit tests pass. | Medium | Update testing libraries and fix any test failures caused by updates. | Medium - Ensures application tests are relevant and accurate.
Run Application Locally | Test the application locally and identify runtime issues. | High | Run the application locally and debug runtime errors. | High - Validates application behavior in the local environment.
Test with AOT Compilation | Ensure Ahead-of-Time (AOT) compilation works without errors. | High | Run ng build --prod --aot and fix any compilation errors. | High - Ensures build success and optimal runtime performance.
Cross-Browser Testing | Test the application in all supported browsers for compatibility. | Medium | Test application functionality on all targeted browsers. | Medium - Prevents browser-specific issues post-upgrade.
Run Unit Tests | Execute all unit tests and ensure they pass. | High | Run ng test and resolve any test failures. | High - Confirms application stability through automated tests.
Update CI/CD Pipelines | Update CI/CD pipelines to reflect Angular 17 configurations. | Medium | Update CI/CD configurations for Angular 17 compatibility. | Medium - Ensures build pipelines remain operational post-upgrade.
Deploy to a DEV Environment | Deploy the application to a DEV environment for validation. | High | Deploy the updated application to a staging environment for review. | High - Validates changes before production deployment.
Perform Final Regression Testing | Perform final regression testing to ensure functionality across all features. | High | Run thorough regression testing to ensure application stability. | High - Ensures stability across all features and modules.
Deploy to Production | Deploy the updated application to production. | High | Deploy the application to production servers. | High - Final step to make the upgrade available to users.
Update Documentation | Update internal and external documentation to reflect the changes. | Medium | Update documentation to include Angular 17 changes and new features. | Low - Provides clarity on changes and future upgrades.

## Potential Changes
Breaking Changes | Major version upgrades often introduce breaking changes. We need to refactor code and resolve any conflicts arising from these changes.
Dependency Conflicts | Updating dependencies might lead to conflicts between different libraries. We need to manage dependencies and resolve conflicts using tools like npm audit fix.
Custom Code | Heavily customized code or reliance on undocumented features might pose challenges during migration. Refactor such code to align with Angular 17 best practices.